**Timeline**

**August:** Compile list of Engineers and contact details, establish communications with STEM organisations.

**September:**  Contact schools and FE colleges. Create calendar of all planned STEM events.

**End September/ early October**: 2 workshops - > Bespoke Communications (Belfast & Derry)

**October:** Engineers begin making videos ‘I am an Engineer’ (a pilot/ biomedical engineer)

**October:** Disseminate Calendar of STEM events to Engineers

**October:** Signups Complete, Engineers begin to write blogs

**November until April:** Outreach begins

Upload videos and blogs to website

**May/ June:** Engineers meet together for a final evaluation session